## Slide 1: Mid-Term Project Status LIQUID: 2-D FLUID DYNAMIC SIMULATOR
TEAM PRYMM
Pavan Kumar Gade, Radhika Panchal, Yashraj Sinha, Minghua Liu and Manoj Mathe

## Slide 2: Architecture Diagram

## Slide 3: Current Status of each component
Components | Percentage Completion
User Interface Subsystem | 90
Input Processing | 70
Configuration Update Subsystem | 70
Rendering Engine Subsystem | 50
Log Retrieval subsystem and Logging Subsystem | 10
Maintenance | 0

## Slide 4: Current status of project task
User Interface subsystem
    GUI design : 90 %
    Configuration Settings: 90%
Rendering Engine subsystem
    Calculation of fluid Particles : 50%
    Pipe settings and Initial force influence : 20%
Log subsystem
    Write log : 10% - GUI for writing log implemented
    Retrieve log : 10% - GUI for retrieve log implemented
Maintenance
    Log size monitoring : 0%
Installable Feature
    Make application installable on MS Windows platform : 0%
Documentation
    User Manual, Programmer guide : 0%

## Slide 5: Technical and Scheduling area of concern
Technical areas of concern
None
Scheduling areas of concern
In time implementation with correct calculations to simulate flow of fluid from all four directions.

## Slide 6: Remaining Task Schedule
User Interface - Add flow meter
(Radhika Panchal :17th to 25th November 2015)
Log - Write break point , flow meter and configuration in log file
(Pavan Kumar Gade and Manoj Mathe: 17th to 29th November 2015)
Log - Retrieve log file and perform configuration settings accordingly
(Pavan Kumar Gade and Manoj Mathe:17th to 29th November 2015)
Maintenance – Tracking size of log file
(Minghua Liu : 03rd to 5th December 2015)
Rendering - Fluid flow from all directions of container and impact of adding pipe at entry and exit path
(Yashraj Sinha : 17th to 29th November 2015)
Installable feature : Make the application installable on MS Windows.
(Minghua Liu : 05th to 09th December 2015)
Documentation – Preparation of User guide, Installation guide and Programmer guide
(Team PRYMM from 11th to 13th December 2015)
Integration and System Test : After every feature integration and before major milestones.
(Yashraj Sinha and Minghua Liu

## Slide 7: Thank You